## Sheet1
CIMT 2025 DEADLINES
Item | Who's Responsible | E-kit | Deadline Date | Location
List of Exhibits | Shell Scheme and Raw Space | CIMT Exhibitor's Entrance | 2025-01-15 | Exhibitor Manual Filling
AMT USA Pavilion Directory Listing | Shell Scheme and Raw Space | AMT Pavilion Page | 2025-02-28 | Exhibitor Manual (e-kit)
Exhibition Catalogue | Shell Scheme and Raw Space | CIMT Exhibitor's Entrance | 2025-02-28 | Exhibitor Manual Filling
Form 2: Application Form for Rental Items and Price list (includes furniture, electrical, Water and Compressed Air, Internet and Telephone) | Optional | CIMT Exhibitor's Entrance | 2025-03-03 | Technical Orders/Build a Declaration Portal
Form 3: Construction Application Form for Raw Space | Raw Space | CIMT Exhibitor's Entrance | 2025-03-03 | Technical Orders/Build a Declaration Portal
Form 4: Raw Space Letter of Undertaking for Exhibitor | Raw Space | CIMT Exhibitor's Entrance | 2025-03-03 | Technical Orders/Build a Declaration Portal
Form 5: Raw Space Letter of Undertaking of Pointed Contractor | Raw Space | CIMT Exhibitor's Entrance | 2025-03-03 | Technical Orders/Build a Declaration Portal
Form 6: Raw Space Letter of Undertaking for Contractor | Raw Space | CIMT Exhibitor's Entrance | 2025-03-03 | Technical Orders/Build a Declaration Portal
Form 7: Raw Space Letter of Undertaking for Double Storey | Raw Space | CIMT Exhibitor's Entrance | 2025-03-03 | Technical Orders/Build a Declaration Portal
Form 8: Agreement on handling breach of contract for booth construction | Raw Space | CIMT Exhibitor's Entrance | 2025-03-03 | Technical Orders/Build a Declaration Portal
Upload Drawings (Raw Space Exhibitors only) | Raw Space | CIMT Exhibitor's Entrance | 2025-03-03 | Technical Orders/Build a Declaration Portal
Logo for Shell Scheme counter | Shell Scheme | Beijing M.H.TALE Expo Co., Ltd LINK | 2025-03-03 | Link emailed seperately
Exhibitor’s Badge | Shell Scheme and Raw Space | CIMT Exhibitor's Entrance | 2025-03-14 | Exhibitor Manual Filling
Advertising and Promotion | Optional | CIMT Exhibitor's Entrance | 2025-03-21 | Exhibitor Manual Filling
Invitation Letter for Visa | Optional | CIMT Exhibitor's Entrance | 2025-03-21 | Exhibitor Manual Filling
Technical Exchange Seminar | Optional | CIMT Exhibitor's Entrance | 2025-04-10 | Exhibitor Manual Filling
Visitor Invitation | Optional | CIMT Exhibitor's Entrance | no deadline | Exhibitor Manual Filling